ShipBridge

Pilot-to-Production Platform

Day-by-Day Build Plan · 30-Day Roadmap · Component Inventory

| Product | ShipBridge v0.1.0 |
| --- | --- |
| Stack | Next.js 15 · FastAPI · PostgreSQL · Redis · Temporal · Railway · Vercel |
| Timeline | 6 weeks · 30 working days |
| Team size | Solo founder (Biswadeepak) |
| ICP | Engineering leads · DevOps teams with AI agents stuck in pilot |

# Table of Contents

Week 1 — Foundation & Project Scaffold (Days 1–5)

Week 2 — Assessment Engine (Days 6–10)

Week 3 — Integration OS: Connector Registry (Days 11–15)

Week 4 — Integration OS: Context Assembly + Event Layer (Days 16–20)

Week 5 — Governance Toolkit + Staged Deployer (Days 21–25)

Week 6 — Polish, Security, Launch (Days 26–30)

Appendix A — Component Inventory

Appendix B — Tech Stack Reference

# Week 1 — Foundation & Project Scaffold

| Day | Tasks & Deliverable |
| --- | --- |
| Day 1 Project Bootstrap | Tasks |
|  | → Initialise Next.js 15 monorepo (app router, TypeScript strict) |
|  | → Create FastAPI service skeleton with async lifespan, health endpoint |
|  | → Provision Supabase project: enable pgvector, set wal_level=logical |
|  | → Configure Railway project: FastAPI + Redis + Temporal worker services |
|  | → Set up Vercel project for Next.js frontend with preview branches |
|  | → Create GitHub repo, branch protection rules, PR template |
|  | → Configure environment variables: Supabase, Redis, Anthropic API key |
|  | Deliverable: All services boot, health checks green in CI |
| Day 2 Auth & Multi-Tenancy | Tasks |
|  | → Implement Supabase Auth with email + Google OAuth |
|  | → Create tenants, users, memberships tables with RLS policies |
|  | → Add tenant_id to every table — enforce in all queries |
|  | → Build JWT middleware for FastAPI: extract tenant_id from token |
|  | → Create API key table: HMAC-stored, scoped (read / write / admin) |
|  | → Build /auth/exchange endpoint: swap Supabase JWT for internal session |
|  | → Add tenant context React provider: useCurrentTenant() hook |
|  | Deliverable: Auth flow end-to-end: sign up, sign in, API key generation |
| Day 3 Database Schema v1 | Tasks |
|  | → Create projects table (tenant_id, name, framework, stack_json) |
|  | → Create assessment_runs table (project_id, scores_json, gap_report_json) |
|  | → Create connectors table (tenant_id, name, auth_type, credentials_vault_ref) |
|  | → Create connector_health table (connector_id, status, latency_ms, checked_at) |
|  | → Create normalization_rules table (app, trigger, payload_map, status, version) |
|  | → Create agent_events table (partitioned by tenant_id, dedup_key index) |
|  | → Create event_subscriptions table (tenant_id, event_type, filter_jmespath, agent_id) |
|  | → Run Alembic migration, seed dev data fixtures |
|  | Deliverable: Full schema migrated, fixtures loadable with make seed |
| Day 4 CI/CD & Observability | Tasks |
|  | → Configure GitHub Actions: lint, type-check, test, build on every PR |
|  | → Set up pytest + httpx for FastAPI integration tests |
|  | → Set up Vitest for Next.js unit tests |
|  | → Integrate OpenTelemetry SDK into FastAPI (traces + metrics) |
|  | → Configure OTLP exporter → Grafana Cloud (or self-hosted) |
|  | → Add structured JSON logging (tenant_id, trace_id on every log line) |
|  | → Set up Sentry for error tracking in both services |
|  | → Create Makefile: make dev, make test, make migrate, make seed |
|  | Deliverable: CI green, traces visible in Grafana, Sentry receiving events |
| Day 5 Dashboard Shell | Tasks |
|  | → Build sidebar layout with NavItem, project switcher, readiness score pill |
|  | → Implement tab routing: overview / connectors / events / deployments |
|  | → Build header component with project context + action buttons |
|  | → Add Instrument Sans + JetBrains Mono via Bunny Fonts (self-hosted, GDPR) |
|  | → Implement Jura font for label/category text |
|  | → Create design token file: Measured Signal color system (s0–s4, T.sig, etc) |
|  | → Add Framer Motion: slideUp page transition, pillar card spring physics |
|  | → Create ScoreArc component with threshold marker at 75 |
|  | Deliverable: Dashboard shell renders with all four tabs, correct fonts loaded |

# Week 2 — Assessment Engine

| Day | Tasks & Deliverable |
| --- | --- |
| Day 6 Assessment Engine — Core | Tasks |
|  | → Build AssessmentRunner FastAPI service: accepts project config payload |
|  | → Implement 5-pillar scoring framework (Reliability, Cost, Security, Eval, Governance) |
|  | → Create ReliabilityScorer: parse agent framework config, score compound accuracy |
|  | → Create SecurityScorer: check MCP endpoint auth, prompt injection surfaces |
|  | → Create EvalScorer: detect CI grader presence, test coverage signals |
|  | → Create GovernanceScorer: audit trail presence, HITL gate detection |
|  | → Create CostScorer: model routing analysis, semantic cache presence check |
|  | Deliverable: POST /assess returns scored JSON for a test LangGraph project |
| Day 7 Assessment Engine — Gap Report | Tasks |
|  | → Build GapReport generator: rank blockers by severity × effort matrix |
|  | → Add issue descriptions: each blocker has title, evidence, fix_hint, effort_days |
|  | → Create ReadinessGate: totalScore < 75 → blocked, generate remediation plan |
|  | → Store assessment_run with full scores + gap_report in Postgres |
|  | → Build /api/projects/{id}/assess endpoint (async Celery task) |
|  | → Add SSE endpoint /api/projects/{id}/assess/stream for live progress |
|  | → Integrate assessment results into Overview tab pillar cards + drill-down |
|  | Deliverable: Full assessment run visible in dashboard with drill-down issues list |
| Day 8 Assessment Engine — GitHub App | Tasks |
|  | → Register GitHub App with webhooks: push, pull_request events |
|  | → Implement webhook receiver: verify X-Hub-Signature-256, queue to Redis |
|  | → Build PR comment poster: post readiness score as structured comment on open PRs |
|  | → Add readiness badge endpoint: SVG badge at /badge/{project_id} |
|  | → Create GitHub App installation flow in dashboard settings |
|  | → Add framework auto-detection: scan repo for LangGraph / CrewAI / AutoGen / n8n |
|  | → Implement delta scoring: show score change vs last commit |
|  | Deliverable: GitHub App posts score badge on PR within 60s of commit |
| Day 9 Eval Harness Builder | Tasks |
|  | → Build EvalHarnessGenerator: accepts agent definition, produces test suite |
|  | → Implement LLM-as-judge grader template generator (Haiku, structured output) |
|  | → Create CI gate template: GitHub Actions YAML with score threshold check |
|  | → Build DatasetSeeder: extract 20 representative inputs from pilot trace logs |
|  | → Create BaselineCapture: run agent against seed dataset, store as golden baseline |
|  | → Add eval_runs table: run_id, scores_json, baseline_delta, triggered_by |
|  | → Wire eval score into assessment Eval pillar (auto-updates on each run) |
|  | Deliverable: Eval harness generated, baseline captured, CI gate template downloadable |
| Day 10 Cost + Token Modeler | Tasks |
|  | → Build CostModeler service: accepts model config + monthly task volume |
|  | → Add model pricing table (Haiku / Sonnet / Opus per 1M tokens, updated monthly) |
|  | → Implement 3-tier routing optimizer: classify tasks → cheapest capable model |
|  | → Build SemanticCacheEstimator: estimate hit rate from task diversity score |
|  | → Create production cost projection: 1x, 10x, 100x scale scenarios |
|  | → Add cost breakdown chart to dashboard (recharts, per-model breakdown) |
|  | → Wire cost score into assessment Cost pillar |
|  | Deliverable: Cost projection visible in dashboard with scale selector |

# Week 3 — Integration OS: Connector Registry

| Day | Tasks & Deliverable |
| --- | --- |
| Day 11 ConnectorAdapter Interface | Tasks |
|  | → Define ConnectorAdapter abstract base class: fetch(), health_check(), normalize() |
|  | → Implement OAuthVault: store refresh tokens in Supabase Vault (AES-256) |
|  | → Build token refresh scheduler: Celery beat, proactive refresh 5min before expiry |
|  | → Create CircuitBreaker class: 3 states, Redis state store, 5 fail → open, 30s recovery |
|  | → Build ConnectorRegistry: lookup by (tenant_id, name), Redis cache 1h TTL |
|  | → Implement connector_health background job: ping every 60s, write latency to DB |
|  | → Build /api/connectors CRUD endpoints (list, create, test, delete) |
|  | Deliverable: ConnectorRegistry boots, circuit breaker state visible per connector |
| Day 12 Salesforce + Notion Adapters | Tasks |
|  | → Implement SalesforceAdapter: OAuth2 PKCE flow, normalize() → agent-friendly markdown |
|  | → Support Salesforce queries: opportunity, account, contact, activity objects |
|  | → Implement NotionAdapter: OAuth2, normalize() for pages, databases, blocks |
|  | → Add Notion database query support with filter + sort parameter mapping |
|  | → Write normalize() unit tests: raw API JSON → expected markdown output assertions |
|  | → Add connector card to dashboard Connectors tab: status, latency, rule version |
|  | → Add OAuth connection UI: authorize button, token status, revoke button |
|  | Deliverable: Salesforce + Notion connectors authorize and return normalized data |
| Day 13 Slack + HubSpot + Stripe Adapters | Tasks |
|  | → Implement SlackAdapter: Bot token auth, normalize messages/threads/channel info |
|  | → Implement HubSpotAdapter: OAuth2, normalize contacts/companies/deals/activities |
|  | → Implement StripeAdapter: API key auth, normalize payments/customers/subscriptions |
|  | → Add rate limit handling to all adapters: 429 → exponential backoff → circuit trip |
|  | → Add per-adapter request timeout: 5s default, configurable per connector |
|  | → Write integration tests for all 5 adapters against sandbox/test accounts |
|  | → Update Connectors dashboard tab: 5 connectors show health + latency sparkline |
|  | Deliverable: 5 production adapters functional with real OAuth connections |
| Day 14 GitHub + Linear + Airtable Adapters | Tasks |
|  | → Implement GitHubAdapter: GitHub App auth, normalize repos/issues/PRs/commits |
|  | → Implement LinearAdapter: API key auth, normalize issues/projects/cycles/comments |
|  | → Implement AirtableAdapter: Personal token auth, normalize tables/records/fields |
|  | → Add Google Workspace adapter: OAuth2, normalize Drive files + Gmail threads |
|  | → Add Postgres direct adapter: connection string, normalize query results |
|  | → Build adapter plugin registry: dynamic load by name string |
|  | → Update connector dashboard: 10 total adapters, health dashboard overview |
|  | Deliverable: Full 10-adapter build complete, all health checks green |
| Day 15 Composio Long-Tail Integration | Tasks |
|  | → Integrate Composio Python SDK as long-tail connector backend |
|  | → Build ComposioProxy adapter: wraps Composio, passes through to own normalize() |
|  | → Implement two-layer normalization: Composio schema → NormalizationRule → AgentEvent |
|  | → Create NormalizationRule table migration (rule_id, app, trigger, payload_map, status) |
|  | → Build RuleRegistry: lookup by (app, trigger), Redis cache with hot-reload |
|  | → Build JMESPathExecutor: apply payload_map to raw Composio payload |
|  | → Add UnknownEventQueue: store unrecognized triggers for offline rule generation |
|  | Deliverable: Composio webhooks arrive, known triggers normalize, unknown queue fills |

# Week 4 — Integration OS: Context Assembly + Event Layer

| Day | Tasks & Deliverable |
| --- | --- |
| Day 16 LLM Rule Generator (Offline) | Tasks |
|  | → Build RuleGeneratorJob: Celery beat, drains UnknownEventQueue every 5 min |
|  | → Fetch Composio trigger schema docs via Composio SDK |
|  | → Implement LLM rule generation prompt (Haiku, structured output → NormalizationRule JSON) |
|  | → Add snapshot test runner: re-apply generated rule against sample payload, assert output |
|  | → Build admin rule review UI: show draft rule + sample payload + diff editor |
|  | → Implement rule promotion flow: draft → active, cache invalidation, hot-reload |
|  | → Add composio_schema_hash: nightly hash comparison, flag needs_review on drift |
|  | Deliverable: Unknown trigger → draft rule generated → admin approves → active in 5min |
| Day 17 Context Assembly — Hybrid Retrieval | Tasks |
|  | → Build ContextAssemblyEngine: accepts ContextRequest, returns AssembledContext |
|  | → Add intent classifier (Haiku, ~50ms): structured / semantic / live / hybrid |
|  | → Implement pgvector dense retrieval: tenant-namespaced embeddings, cosine similarity |
|  | → Add tsvector sparse retrieval (BM25-style): GIN index on content column |
|  | → Implement reciprocal rank fusion: merge dense + sparse result sets |
|  | → Create EmbeddingIngester: chunk documents → embed → store in pgvector namespace |
|  | → Add SHA-256 context cache: Redis 24h TTL, 30-50% expected hit rate |
|  | Deliverable: Hybrid retrieval returning ranked chunks, cache hit rate measurable |
| Day 18 Context Assembly — Re-ranker + Token Budget | Tasks |
|  | → Deploy cross-encoder re-ranker: small BERT model (ms-marco-MiniLM) on Railway |
|  | → Add re-ranker API wrapper: score (query, chunk) pairs, ~100ms p95 |
|  | → Implement relevance threshold filter: drop chunks below 0.6 score |
|  | → Build parent-child retrieval: embed 256-token chunks, retrieve 1024-token parents |
|  | → Implement TokenBudgetEnforcer: compress context to fit step allocation |
|  | → Add retrieval_trace to AssembledContext: which chunks, scores, cache_hit flag |
|  | → Wire context cache hit rate into dashboard cost projection (saved tokens) |
|  | Deliverable: Full context pipeline: intent → hybrid → rerank → prune → deliver |
| Day 19 Event Ingestion — Webhook Receiver | Tasks |
|  | → Build webhook receiver: FastAPI /webhooks/{provider} endpoint |
|  | → Implement HMAC-SHA256 signature verification per provider |
|  | → Add 200ms ACK guarantee: write to Redis Streams, return immediately |
|  | → Implement Redis Streams consumer: process events async, max 10 retries |
|  | → Build DeduplicationEngine: Redis SETNX on dedup_key, 24h TTL |
|  | → Add Dead Letter Queue: exhausted retries → DLQ table with failure reason |
|  | → Implement CDC connector: Postgres WAL logical replication → AgentEvent stream |
|  | Deliverable: Webhooks arrive, deduplicated, written to Redis Streams within 200ms |
| Day 20 Event Ingestion — Subscription Engine + Dashboard | Tasks |
|  | → Build AgentTriggerSubscriptionEngine: match events against subscription JMESPath filters |
|  | → Add debounce_seconds to subscriptions: prevent re-trigger within window |
|  | → Create subscription CRUD API: /api/subscriptions (list, create, update, delete) |
|  | → Build event pipeline dashboard tab: stats strip, live event log table |
|  | → Add real-time event SSE stream: push new events to dashboard as they arrive |
|  | → Add unknown trigger alert to Connectors tab: count + review draft link |
|  | → Wire event volume into connector health dashboard: events/24h per connector |
|  | Deliverable: Full event pipeline visible in dashboard, unknown trigger alert working |

# Week 5 — Governance Toolkit + Staged Deployer

| Day | Tasks & Deliverable |
| --- | --- |
| Day 21 Governance Toolkit — Audit Trail | Tasks |
|  | → Create audit_logs table: immutable append-only (no UPDATE/DELETE RLS) |
|  | → Implement AuditLogger: emit on every tool call, LLM decision, state change |
|  | → Add audit_log FastAPI middleware: capture request/response metadata |
|  | → Build HITL gate abstraction: HumanGate class, configurable trigger conditions |
|  | → Implement HITL approval endpoint: /api/gates/{gate_id}/approve¦reject |
|  | → Create HITL notification: Slack webhook + email on gate trigger |
|  | → Build governance score reporter: wire to assessment Governance pillar |
|  | Deliverable: Every agent action logged, HITL gate blocks and notifies |
| Day 22 Governance Toolkit — Compliance PDF | Tasks |
|  | → Build CompliancePDFGenerator: weasyprint, structured readiness report |
|  | → Add cover page: project name, date, overall score, assessor signature block |
|  | → Include 5-pillar scorecard table with evidence per issue |
|  | → Add audit trail summary: last 7 days agent actions, tool call frequency |
|  | → Include deployment history: stages completed, gate outcomes, rollback events |
|  | → Add GDPR/SOC2 checklist appendix: 20 control checks with pass/fail status |
|  | → Wire PDF generation to Export PDF button in dashboard header |
|  | Deliverable: Full compliance PDF downloadable from dashboard |
| Day 23 Temporal Workflow Setup | Tasks |
|  | → Configure Temporal server on Railway (or Temporal Cloud for managed) |
|  | → Install Temporalio Python SDK in FastAPI service |
|  | → Define StagedDeploymentWorkflow: 4 activities (sandbox, canary5, canary25, prod) |
|  | → Implement WorkflowState persistence: Temporal handles durability + checkpointing |
|  | → Build DeploymentGate activity: check readiness score, assert >= 75 before advance |
|  | → Create WorkflowTrigger endpoint: POST /api/deployments with project_id |
|  | → Add Temporal worker to Railway: separate service, auto-restart on failure |
|  | Deliverable: Temporal workflow starts, sandbox stage activates, gate blocks at <75 |
| Day 24 Staged Deployer — Canary Logic | Tasks |
|  | → Implement SandboxActivity: run agent against isolated test environment |
|  | → Implement Canary5Activity: route 5% traffic, collect metrics for 12h minimum |
|  | → Implement Canary25Activity: route 25%, compare against sandbox baseline |
|  | → Build MetricsCollector: task success rate, latency p95, token cost/task, escalation rate |
|  | → Add auto-rollback trigger: if task success drops >5% vs baseline → rollback workflow |
|  | → Build RollbackActivity: revert to previous stage, notify team via Slack |
|  | → Create deployment_stages table: record each stage outcome with metrics snapshot |
|  | Deliverable: Full 4-stage pipeline runs, auto-rollback triggers on regression |
| Day 25 Deployments Dashboard Tab | Tasks |
|  | → Build deployment stage track UI: 4 nodes with connector progress line |
|  | → Add active stage pulsing indicator with Framer Motion breathe animation |
|  | → Implement canary metrics grid: 4 KPIs with delta vs baseline, colored arrows |
|  | → Add health status badge: healthy / regression / rollback in progress |
|  | → Build deployment history list: past deployments, durations, outcomes |
|  | → Add rollback button: manual rollback to previous stage with confirmation modal |
|  | → Connect deployment tab to Temporal workflow status via SSE |
|  | Deliverable: Deployments tab fully wired to live Temporal workflow state |

# Week 6 — Polish, Security, Launch

| Day | Tasks & Deliverable |
| --- | --- |
| Day 26 Security Hardening | Tasks |
|  | → Add Cloudflare WAF in front of FastAPI and Next.js |
|  | → Implement rate limiting: 100 req/min per tenant on all API routes |
|  | → Add CSRF protection to all state-mutating Next.js routes |
|  | → Audit all Supabase RLS policies: confirm no cross-tenant data leakage |
|  | → Add secrets scanning to CI: detect API keys committed to git |
|  | → Implement webhook payload size limit: reject >1MB payloads |
|  | → Add security scan to assessment engine: prompt injection surface detection |
|  | Deliverable: Security audit checklist passes, WAF active, rate limits enforced |
| Day 27 Billing Integration | Tasks |
|  | → Integrate Stripe: create products for Free / Pro ($29) / Enterprise ($199) plans |
|  | → Build subscription management: Stripe Checkout, portal, webhook handler |
|  | → Implement usage metering: track assessments run, connectors connected, scans/day |
|  | → Add plan enforcement middleware: block over-limit requests with upgrade prompt |
|  | → Build billing page in dashboard settings: current plan, usage, upgrade CTA |
|  | → Add Free tier limits: 1 project, 3 connectors, 5 assessments/month |
|  | → Create trial period: 14 days Pro features on signup |
|  | Deliverable: Billing flow end-to-end: Free signup → upgrade → payment → Pro features |
| Day 28 Onboarding Flow | Tasks |
|  | → Build project creation wizard: name → framework select → stack config → first assess |
|  | → Add empty state screens: each tab has a clear call-to-action when data is absent |
|  | → Create connector quick-connect flow: OAuth popup → success → redirect back to dashboard |
|  | → Build first-assessment celebration: score revealed with animated ScoreArc fill |
|  | → Add contextual help tooltips on all scoring criteria (? icon → explanation) |
|  | → Create sample project with pre-populated data for demo/marketing |
|  | → Add product tour: 5-step Shepherd.js tour on first login |
|  | Deliverable: New user can complete onboarding and first assessment in under 5 minutes |
| Day 29 Performance + Error States | Tasks |
|  | → Add skeleton loading states to all dashboard cards (no layout shift) |
|  | → Implement optimistic UI on pillar card click: immediate visual response |
|  | → Add error boundaries to every React subtree with graceful fallback |
|  | → Implement retry logic on all API calls: 3 retries with exponential backoff |
|  | → Add offline detection banner: yellow alert when API unreachable |
|  | → Run Lighthouse audit: target 90+ performance score on dashboard |
|  | → Add virtual scrolling to event log: handle 10k+ events without frame drops |
|  | Deliverable: Dashboard loads in <1.5s, all error states handled gracefully |
| Day 30 Launch Readiness | Tasks |
|  | → End-to-end test: create project → connect Salesforce → run assessment → fix issue → deploy |
|  | → Load test: 50 concurrent assessments, 1000 req/min connector health checks |
|  | → Set up uptime monitoring: Betterstack or Upptime, 30s checks |
|  | → Write public changelog: v0.1.0 feature list with screenshots |
|  | → Submit GitHub Action to GitHub Marketplace: readiness-gate action |
|  | → Create Product Hunt draft: tagline, description, screenshots, first comment |
|  | → Configure Cloudflare analytics: Real User Monitoring, Core Web Vitals |
|  | Deliverable: Production environment stable, GitHub Action live, PH draft ready |

# Appendix A — Component Inventory

All 29 components, services, and workers to be built across the 6-week plan.

| Layer | Component | File path | Description | Week |
| --- | --- | --- | --- | --- |
| Frontend | ScoreArc | components/ScoreArc.tsx | Radial score ring with 75% threshold marker and animated fill | 1 |
| Frontend | PillarCard | components/PillarCard.tsx | Clickable scoring card with spring physics hover/active states | 1 |
| Frontend | StatusTag | components/StatusTag.tsx | Typographic status labels: healthy, degraded, critical, etc. | 1 |
| Frontend | MicroBar | components/MicroBar.tsx | Inline progress bar for score visualization within pillar cards | 1 |
| Frontend | NavItem | components/NavItem.tsx | Sidebar nav item with active indicator and SVG icon system | 1 |
| Frontend | EventLogTable | components/EventLogTable.tsx | Virtualized event stream with monospace payload preview | 4 |
| Frontend | StageTrack | components/StageTrack.tsx | 4-node deployment pipeline with animated progress connector | 5 |
| Frontend | CanaryMetrics | components/CanaryMetrics.tsx | 4-KPI grid comparing canary vs baseline with delta indicators | 5 |
| Frontend | ConnectorCard | components/ConnectorCard.tsx | Connector row with circuit breaker status, latency, rule version | 3 |
| Frontend | RuleReviewUI | components/RuleReviewUI.tsx | Admin diff editor for approving LLM-generated NormalizationRules | 4 |
| API | AssessmentRunner | api/assessment/runner.py | Orchestrates all 5 pillar scorers, returns GapReport | 2 |
| API | ReliabilityScorer | api/assessment/scorers.py | Scores compound accuracy, retry logic, circuit breaker presence | 2 |
| API | CostScorer | api/assessment/scorers.py | Analyses model routing, semantic cache, projects production cost | 2 |
| API | SecurityScorer | api/assessment/scorers.py | Detects unauthenticated MCP endpoints, prompt injection surfaces | 2 |
| API | EvalScorer | api/assessment/scorers.py | Detects CI grader presence, baseline existence, test coverage | 2 |
| API | GovernanceScorer | api/assessment/scorers.py | Checks audit trail, HITL gate configuration, ownership records | 2 |
| API | WebhookReceiver | api/events/webhooks.py | HMAC-verified inbound webhook endpoint, 200ms ACK guarantee | 4 |
| API | JMESPathExecutor | api/events/normalizer.py | Applies NormalizationRule payload_map to raw Composio payloads | 3 |
| API | ContextAssemblyEngine | api/os/context.py | Intent classifier → hybrid retrieval → rerank → token budget | 4 |
| API | CompliancePDFGenerator | api/governance/pdf.py | Generates downloadable compliance report with scoring evidence | 5 |
| Workers | RuleGeneratorJob | workers/rule_gen.py | Celery beat: drains unknown queue, calls LLM, creates draft rules | 4 |
| Workers | ConnectorHealthJob | workers/connector_health.py | Pings each connector every 60s, writes latency to DB | 3 |
| Workers | SchemaHashJob | workers/schema_hash.py | Nightly Composio schema hash comparison, flags drift | 4 |
| Workers | StagedDeploymentWorkflow | workers/temporal_workflows.py | Temporal: sandbox → canary5 → canary25 → production, auto-rollback | 5 |
| Data | RuleRegistry | data/rule_registry.py | NormalizationRule lookup by (app, trigger), Redis cache, hot-reload | 3 |
| Data | OAuthVault | data/vault.py | Supabase Vault AES-256 for refresh tokens, proactive rotation | 3 |
| Data | CircuitBreaker | data/circuit_breaker.py | 3-state FSM per connector in Redis: closed/open/half-open | 3 |
| Data | DeduplicationEngine | data/dedup.py | Redis SETNX on dedup_key, 24h TTL, prevents duplicate agent triggers | 4 |
| Data | AuditLogger | data/audit.py | Immutable append-only audit log, RLS prevents delete/update | 5 |

# Appendix B — Tech Stack Reference

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend | Next.js 15 (App Router) | RSC + streaming, Vercel-native deployment, edge-ready |
| Frontend | Framer Motion | Spring physics animations for pillar cards and ScoreArc |
| Frontend | JetBrains Mono / Instrument Sans | Monospace for data; geometric sans for structure (Bunny Fonts CDN) |
| Backend | FastAPI (Python 3.12) | Async, type-safe, OpenAPI auto-generation, native OTLP support |
| Backend | Celery + Redis | Background jobs: connector health, rule gen, schema hash checks |
| Backend | Temporal | Durable staged deployment workflow with step-level checkpointing |
| Data | PostgreSQL + pgvector | RLS multi-tenancy, vector search, WAL CDC, ACID guarantees |
| Data | Supabase | Managed Postgres + Auth + Vault (AES-256 cred storage) |
| Data | Redis Streams | Event bus: webhook ingestion, dedup, subscription matching |
| Infra | Railway | FastAPI, Celery workers, Temporal worker, Redis, re-ranker model |
| Infra | Vercel | Next.js edge deployment, preview branches per PR |
| Infra | Cloudflare | WAF, CDN, DDoS protection, Real User Monitoring |
| Integrations | Composio (27k stars) | Long-tail connector adapters beyond top-10 hand-built set |
| Integrations | Stripe | Billing: Free / Pro $29 / Enterprise $199 plans + usage metering |
| Integrations | GitHub App | PR comment score badges, repo framework detection |
| Observability | OpenTelemetry + Grafana | Traces, metrics, structured logs across all services |
| Observability | Sentry | Error tracking with tenant_id context in both services |